## Overview (Read First)
#VALUE!
The Risk Register serves as the central supervisory log for AI governance. While Tools 1 and 2 identify risks, the Risk Register documents them, assigns responsibility, tracks mitigation, and records evidence that risks have been addressed. It is both a governance tool and an accountability mechanism.
While developed for social assistance use cases, this tool is adaptable for broader use across social protection pillars and other public-sector domains.
Sources and Methodology
This tool adapts established risk register practices from multiple domains for AI governance in social protection:
Humanitarian data governance: The structure reflects the iterative, lifecycle-based approach to risk management in the Handbook on Data Protection in Humanitarian Action (ICRC, 2024), which emphasises that DPIAs and risk assessments should be "continuous processes" that follow a system "throughout its life cycle" (Chapter 17.6). The Handbook's guidance on documenting data controller/processor relationships, liability allocation, and contractual safeguards informs the register's accountability fields.
Humanitarian data responsibility: The OCHA Data Responsibility Guidelines (OCHA, 2025) inform the register's approach to tracking data-related risks, mitigation measures, and incident response procedures.
Project risk management: The tool adapts standard project risk register practices (likelihood, impact, mitigation, owner, status) while adding AI-specific categories such as model behaviour, bias monitoring, human oversight arrangements, and rights impacts.
Purpose and Use
Good practice is to record all risks that emerge from the intrinsic and context assessments (Tools 1 and 2), as well as those identified through DPIAs or AIAs, audits, testing, stakeholder feedback, and ongoing monitoring. Each entry should include:
1. A short description of the risk
2. Its likelihood and severity
3. The rights it affects
4. Any link to CRM governance factors
5. The mitigation required
6. The team responsible
7. A timeline
8. Evidence that will confirm when the risk is resolved
The register should remain active throughout the system's lifecycle and be updated whenever new risks appear, when conditions change, or when mitigation measures are complete.

## Risk Register
#VALUE!
Risk ID | AI Use Case | Source | Risk Description | Intrinsic Severity | Likelihood | Overall Risk Rating | Mitigation Required | Responsibility (Owner) | Deadline | Status | Verification Evidence | Notes | Decision Implication
Example 01 | Eligibility Prediction Model | Tool 1 – Intrinsic Risk Worksheet | Model may misclassify eligible households as ineligible due to biased or incomplete training data. | High | Medium | High | Bias audit; HITL review for all eligibility decisions; improve data quality. | Programme Manager / Data Protection Officer | 2025-12-15 | Open | Bias audit report; HITL protocol documentation; retrained model validation results | Critical before pilot. | Blocking
Example 02 | Cross-Registry Entity Resolution | Tool 2 – CRM Diagnostic | Weak legal basis for data linkage across ministries may result in unlawful data processing. | Medium | High | High | Clarify lawful basis; update data-sharing agreements; conduct DPIA. | Legal Unit / Data Governance Lead | 2026-01-10 | In Progress | Signed data-sharing agreements; completed DPIA; legal opinion on lawful basis | Must be resolved before scale-up. | Blocking
Example 03 | Chatbot for Grievance Support | Other (UX Testing) | Users may misunderstand responses due to inconsistent translations or hallucinated outputs. | Low | Medium | Medium | Expand testing; add HITL escalation; publish chatbot limitations. | Service Delivery Unit | 2025-12-05 | Open | UX test results; HITL escalation workflow documentation; published chatbot limitations notice | Safe to pilot with enhanced monitoring. | Monitor
Example 04 | Payment Anomaly Detection | Tool 1 | Model flags legitimate transactions as fraudulent, causing payment delays | Medium | Medium | Medium | Tune alert thresholds; add HITL review before suspension; track false positive rate | Programme Manager / IT Lead | 2026-03-15 | Open | False positive rate analysis; threshold calibration report; HITL suspension review protocol | Acceptable for pilot with enhanced monitoring | Pilot Condition
Example 05 | Chatbot FAQ Module | Other (User Feedback) | Chatbot occasionally provides outdated information on payment schedules | Low | Low | Low | Update knowledge base monthly; add disclaimer to responses | Service Delivery Unit | 2026-02-28 | Open | Monthly knowledge base update log; user feedback summary; disclaimer text confirmation | Low risk, routine tracking sufficient | Monitor

## Mitigation Tracker
#VALUE!
Risk ID | Mitigation Action | Responsible Unit | Status | % Progress | Dependencies | Pre-Go Requirement? | Notes
Example 01 | Conduct full bias audit; retrain model with corrected dataset; introduce HITL verification for all eligibility decisions | Programme Team; Data Science Unit | In Progress | 40% | Training data documentation; recruitment of reviewers | Yes | Critical for beneficiary rights protection
Example 02 | Clarify lawful basis for cross-registry linkage; update DSAs; complete DPIA | Law & Policy Division; Data Governance Lead | In Progress | 60% | Inter-ministerial approval; DPIA consultant availability | Yes | Must be completed before scale-up
Example 03 | Expand multilingual UX testing; add human escalation workflow; publish chatbot limitations | Service Delivery Unit | Open | 10% | Language review; BOT configuration | No | Safe to pilot with stronger monitoring
Example 04 | Tune alert thresholds; add HITL review before any payment suspension; establish false positive tracking | Programme Team; IT Lead | Open | 0.2 | Baseline false positive rate analysis; HITL reviewer assignment | Yes | Must be resolved before pilot proceeds to scale
Example 05 | Establish monthly knowledge base update cycle; add disclaimer to chatbot responses; monitor user feedback | Service Delivery Unit | Open | 0.1 | Content review schedule; feedback channel setup | No | Low risk, routine monitoring sufficient

## Evidence Log
#VALUE!
Risk ID | Evidence Type | File Path / Hyperlink | Date Received | Verified By | Notes
Example 01 | Bias Audit Report | /path/reports/bias_audit_2025.pdf | 2025-11-22 | Data Protection Officer | Preliminary audit complete; further sampling required
Example 01 | Training Data Documentation | /path/data/doc_training_set_v4.docx | 2025-11-20 | Data Manager | Needs additional metadata for 2019–2020 records
Example 02 | Revised Data Sharing Agreement | /path/legal/DSA_v3_draft.pdf | 2025-12-01 | Legal Lead | Awaiting signature from Ministry of Interior
Example 02 | DPIA Draft | /path/dpia/DPIA_cross_registry_v1.docx | 2025-11-28 | Privacy Officer | High-level risks identified; mitigation actions pending
Example 03 | UX Test Results | /path/ux/UX_testing_round2.xlsx | 2025-11-18 | UX Lead | Users struggling with Amharic translation
Example 03 | Chatbot Logs | /path/logs/chatbot_log_export.zip | 2025-11-21 | IT Systems Analyst | Hallucinations detected in 3.2% of responses

## Change Log
#VALUE!
Date | What Changed | Who Changed It | Reason for Change | Version
2025-11-25 | Updated mitigation actions for Example 01 (added retraining requirement) | Programme Manager | Bias audit findings required stronger corrective action | v1.1
2025-11-27 | Added new evidence records for Example 02 (DPIA draft uploaded) | Data Governance Lead | Supporting documents received | v1.2
2025-11-29 | Revised chatbot mitigation plan for Example 03 (HITL escalation added) | Service Delivery Lead | UX test results indicated misunderstanding issues | v1.3